## Revet SCH Detail
U.S. ARMY CORPS OF ENGINEERS MEMPHIS, VICKSBURG, AND NEW ORLEANS REGIONAL REVETMENT ACM SCHEDULE - FY24-25
C&S, GRADING BY MEMPHIS / SINKING BY VICKSBURG
SCHEDULE IS SUBJECT TO CHANGE THROUGHOUT THE SEASON
LAST UPDATE: 10 JUL 2024
MILE AHP | BANK | DISTANCE | DISTRICT | LOCATIONS | Helper Column | TYPE WORK | C&S START | C&S FINISH | GRADING START | GRADING FINISH | GRADING CY's | SINKING LINEAR FEET ACM | SINKING GROSS SQUARES | START | FINISH | LOCATIONS | TRAFFIC RESTRICTIONS
MISSISSIPPI RIVER
437.0 |  |  |  | MSU Onboarding | MSU Onboarding1 | [8 empty] | 2024-08-26 | 2024-08-26 | VICKSBURG HARBOR
|  |  |  | TOW | [9 empty] | 2024-08-27 | 2024-08-31 | TOW
908 | R | -471 | MVM | Milton Bell | Milton Bell1 | [6 empty] | 2100 | 4900 | 2024-09-01 | 2024-09-06 | Milton Bell
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-09-07 | 2024-09-08 | OFF DAYS
775 | R | 133 | MVM | Sunrise | Sunrise1 | [6 empty] | 2100 | 4775 | 2024-09-09 | 2024-09-13 | Sunrise
|  |  |  | TOW | [9 empty] | 2024-09-14 | 2024-09-14 | TOW
535.1 | L | 239.9 | MVK | Island 84 | Island 841 | [6 empty] | 1250 | 5000 | 2024-09-15 | 2024-09-19 | Island 84
|  |  |  | TOW | [9 empty] | 2024-09-20 | 2024-09-20 | TOW
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-09-21 | 2024-09-22 | OFF DAYS
453.6 | R | 81.5 | MVK | Milliken Bend | [7 empty] | 975 | 3800 | 2024-09-23 | 2024-09-26 | Milliken Bend
411.5 | R | 42.1 | MVK | Point Pleasant | Point Pleasant1 | [6 empty] | 2375 | 9500 | 2024-09-27 | 2024-10-04 | Point Pleasant
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-10-05 | 2024-10-06 | TOW
411.5 | R |  | MVK | Point Pleasant | Point Pleasant2 | [8 empty] | 2024-10-07 | 2024-10-07 | Point Pleasant
407.5 | L | 4 | MVK | Grand Gulf | Grand Gulf1 | [6 empty] | 850 | 3400 | 2024-10-08 | 2024-10-10 | Grand Gulf
|  |  |  | TOW | [9 empty] | 2024-10-11 | 2024-10-11
268.5 | R | 143 | MVN | Red Store Landing | [7 empty] | 750 | 9250 | 2024-10-12 | 2024-10-18 | Red Store Landing
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-10-19 | 2024-10-20 | OFF DAYS
249.2 | R | 19.3 | MVN | Arbroth | [7 empty] | 1100 | 12500 | 2024-10-21 | 2024-10-29 | Arbroth
|  |  |  | TOW | [9 empty] | 2024-10-30 | 2024-10-30
148.8 | R | 100.4 | MVN | Vacherie | [7 empty] | 2500 | 16950 | 2024-10-31 | 2024-11-01 | Vacherie
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-11-02 | 2024-11-03
148.8 | R |  | MVN | Vacherie | [9 empty] | 2024-11-04 | 2024-11-13 | Vacherie
|  |  |  | TOW | [9 empty] | 2024-11-14 | 2024-11-14 | TOW
87.4 | R | 61.4 | MVN | Cutoff | Cutoff1 | [6 empty] | 1500 | 19600 | 2024-11-15 | 2024-11-15 | Cutoff
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-11-16 | 2024-11-17 | OFF DAYS
87.4 | R |  | MVN | Cutoff | Cutoff2 | [8 empty] | 2024-11-18 | 2024-11-29 | Cutoff
|  |  |  | NO WORK FOR MSU - OFF DAYS | [9 empty] | 2024-11-30 | 2024-12-01 | OFF DAYS
87.4 | R |  | MVN | Cutoff | Cutoff3 | [8 empty] | 2024-12-02 | 2024-12-02
80.5 | L | 6.9 | MVN | Poydras | [7 empty] | 1150 | 11980 | 2024-12-03 | 2024-12-11 | Poydras
|  |  |  | TOW TO VICKSBURG HARBOR | [9 empty] | 2024-12-12 | 2024-12-15 | TOW
437 |  | -356.5 |  | VICKSBURG HARBOR | [9 empty] | 2024-12-16 | 2024-12-16 | VICKSBURG HARBOR
[9 empty] | DISTRICT |  | CY's | LIN. FT | SQUARES
[9 empty] | MVM |  | 0 | 4200 | 9675
[9 empty] | MVK |  | 0 | 5450 | 21700
[9 empty] | MVN |  | 0 | 7000 | 70280
[9 empty] | REGIONAL TOTAL |  | 0 | 16650 | 101655
|  |  | Mile | Reference Locations
|  |  | 955 | Cairo, IL
|  |  | 889 | New Madrid, MO
|  |  | 847 | Caruthersville, MO
|  |  | 769 | Richardson Landing Casting Field
|  |  | 735 | Memphis, TN
|  |  | 663 | Helena, AR
|  |  | 537 | Greenville, MS
|  |  | 438 | Delta Point Casting Field
|  |  | 437 | Vicksburg, MS
|  |  | 364 | Natchez, MS
|  |  | 304 | Old River Locks
|  |  | 265 | St Francisville Casting Field
|  |  | 230 | Baton Rouge, LA
|  |  | 95 | New Orleans, LA
[15 empty] | 10 | Venice, LA
Formulas:
FINISH = [START]
FINISH = [START]+4
START = [FINISH, row above]+1

## Revet SCH Summary
U.S. ARMY CORPS OF ENGINEERS MEMPHIS, VICKSBURG, AND NEW ORLEANS REGIONAL REVETMENT ACM SCHEDULE - FY23-24
C&S, GRADING BY MEMPHIS / SINKING BY VICKSBURG
SCHEDULE IS SUBJECT TO CHANGE THROUGHOUT THE SEASON
LAST UPDATE: 1 NOVEMBER 2023
MILE AHP | BANK | DISTANCE | DISTRICT | LOCATIONS | TYPE WORK | C&S START | C&S FINISH | GRADING START | GRADING FINISH | GRADING CY's | SINKING LINEAR FEET ACM | SINKING GROSS SQUARES | START | FINISH | LOCATIONS | TRAFFIC RESTRICTIONS
MISSISSIPPI RIVER
321.9 |  |  | MVN | Palmetto Bend | Non-ACM - ROCK | #N/A | #N/A | #N/A | #N/A | #N/A
249.2 |  |  | MVN | Arbroth | Non-ACM - ROCK | 0 | 0 | 0 | 0 | 0
437.0 |  |  |  | MSU Onboarding | [8 empty] | 2024-08-26 | 2024-08-26 | VICKSBURG HARBOR
530.6 | R | -93.6 | MVK | Sunnyside | CONST | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A | #N/A | Sunnyside | No restrictions
214.2 | L | 316.4 | MVN | Manchac | M-SUPP | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A | #N/A | Manchac | No vessel transits during working hours. MSU will fold in at night.
199 | L | 15.2 | MVN | St Gabriel | M-SUPP | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A | #N/A | St Gabriel | No deep-draft vessel transits during working hours. MSU will fold in at night.
108 | R | 91 | MVN | Avondale | MAINT |  |  | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Avondale | Deep-draft transits with a slow bell during working hours with one-way traffic for shallow draft traffic. The MSU will extend 600 feet from the bank channel ward during non-work hours.
84.3 | L | 23.7 | MVN | Poydras | M-SUPP | 0 | 0 |  |  |  | 1150 | 11980 | 2024-12-03 | #N/A | Poydras | Transits with slow bell during working hours. MSU not required to fold in at night.
23.1 | L | 61.2 | MVN | Neptune | M-SUPP | #N/A | #N/A |  |  |  | #N/A | #N/A | #N/A | #N/A | Neptune | Deep-draft transits on a slow bell during working hours. MSU not required to fold in.
149.4 | R | -126.3 | MVN | Vacherie | M-SUPP | 0 | 0 | 0 | 0 | 0 | 2500 | 16950 | 2024-10-31 | #N/A | Vacherie | One-way transits restriction during working hours. MSU will fold in at night.
437 |  | -287.6 |  | VICKSBURG HARBOR | [8 empty] | 2024-12-16 |  | VICKSBURG HARBOR
[8 empty] | DISTRICT |  | CY's | LIN. FT | SQUARES
[8 empty] | MVM |  | 0 | 0 | 0
[8 empty] | MVK |  | 0 | #N/A | #N/A
[8 empty] | MVN |  | #N/A | #N/A | #N/A
[8 empty] | REGIONAL TOTAL |  | #N/A | #N/A | #N/A
Yellow shade represents completed work | [13 empty] | Mile | Reference Locations
[14 empty] | 955 | Cairo, IL
[14 empty] | 889 | New Madrid, MO
[14 empty] | 847 | Caruthersville, MO
[14 empty] | 769 | Richardson Landing Casting Field
[14 empty] | 735 | Memphis, TN
[14 empty] | 663 | Helena, AR
[14 empty] | 537 | Greenville, MS
[14 empty] | 438 | Delta Point Casting Field
[14 empty] | 437 | Vicksburg, MS
[14 empty] | 364 | Natchez, MS
[14 empty] | 304 | Old River Locks
[14 empty] | 265 | St Francisville Casting Field
[14 empty] | 230 | Baton Rouge, LA
[14 empty] | 95 | New Orleans, LA
[14 empty] | 10 | Venice, LA
Formulas:
C&S START = VLOOKUP([LOCATIONS],'Revet SCH Detail'!$E7:P38,4,FALSE())
C&S FINISH = VLOOKUP([LOCATIONS],'Revet SCH Detail'!$E7:P38,5,FALSE())
GRADING START = VLOOKUP([LOCATIONS],'Revet SCH Detail'!$E7:P38,6,FALSE())
GRADING FINISH = VLOOKUP([LOCATIONS],'Revet SCH Detail'!$E7:P38,7,FALSE())
START = VLOOKUP([LOCATIONS],'Revet SCH Detail'!E7:P37,11,FALSE())
FINISH = VLOOKUP([LOCATIONS]&COUNTIF('Revet SCH Detail'!$E7:E37,'Revet SCH Summary'!E9),'Revet SCH Detail'!F7:P37,11,FALSE())