## Revetment Schedule w Formulas
U.S. ARMY CORPS OF ENGINEERS, MEMPHIS, VICKSBURG AND NEW ORLEANS | [14 empty] | REVISION DATE
C&S STARTING DATE 10 June 2022 / GRADER STARTING DATE 06 July 2022 / SINKING STARTING DATE 18 JUL 2022 | [14 empty] | 2022-12-15
C&S, GRADING BY KEVIN WILLIAMS / SINKING BY MAURICE GILMORE
REVETMENT OPERATIONS - FY 22-23
LMR MILE | BANK | DISTANCE | LOCATIONS | TYPE WORK | C&S |  | GRADING |  |  | SINKING
[5 empty] | START | FINISH | START | FINISH | CY's | LINEAR FEET ACM | GROSS SQUARES | START | FINISH | LMR MILE | ANTCIPATED TRAFFIC RESTRICTIONS | MLU (ST Francisville, Delta Point, Richardson Landing) | Barge Count | Priority | Top Bank
MILE
437.0 |  |  | MSU conducts training for crew, makes tow / Mandatory Training | [8 empty] | 2022-07-18 | 2022-07-18 | 437.0
TOW | [11 empty] | 2022-07-19 | 2022-07-20
578.6 | R | -141.6 | OZARK M1 | M-SUPP | 2022-06-10 | 2022-06-12 |  |  |  | 3027 | 10169 | 2022-07-21 | 2022-07-29 | 578.6 | One way traffic | RL | 20
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-07-30 | 2022-07-31
578.6 | R |  | OZARK M1 | M-SUPP | [7 empty] | 2022-08-01 | 2022-08-01 | 578.6 | One way traffic
503.5 | R | 75.1 | SARAH ISL-FIRST PASS | M-SUPP | 2022-06-13 | 2022-06-15 |  |  |  | 3000 | 4501 | 2022-08-02 | 2022-08-07 | 503.5 | River closure for southbound traffic > 12 barges during daylight hours | RL | 9
491.7 | R | 11.8 | BALESHED M1 | M-SUPP | 2022-06-16 | 2022-06-22 |  |  |  | 2579 | 7078 | 2022-08-07 | 2022-08-12 | 491.7 | One way traffic | RL | 14
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-08-13 | 2022-08-14
491.7 | R |  | BALESHED M1 | M-SUPP | [7 empty] | 2022-08-15 | 2022-08-16 | 491.7 | One way traffic
428.9 | R | 62.8 | REID BEDFORD M1 | M-SUPP | 2022-06-23 | 2022-06-26 |  |  |  | 1390 | 6219 | 2022-08-17 | 2022-08-24 | 428.9 | One way traffic | RL | 12
345.1 | L | 83.8 | RAILROAD LANDING 2020 M1 | M-SUPP | 2022-07-03 | 2022-07-07 |  |  |  | 3921 | 14608 | 2022-08-25 | 2022-08-26 | 345.1 | One way traffic | SF | 28
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-08-27 | 2022-08-28
345.1 | L |  | RAILROAD LANDING 2020 M1 | M-SUPP | [7 empty] | 2022-08-29 | 2022-09-06 | 345.1 | One way traffic
344.5 | L | 0.6 | RAILROAD LANDING M4 | M-SUPP | 2022-07-08 | 2022-07-09 |  |  |  | 1549 | 7309 | 2022-09-07 | 2022-09-09 | 344.5 | One way traffic | SF | 14
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-09-10 | 2022-09-11
344.5 | L |  | RAILROAD LANDING M4 | M-SUPP | [7 empty] | 2022-09-12 | 2022-09-14 | 344.5 | One way traffic
330.6 | R | 13.9 | BOUGERE | CONST | 2022-07-13 | 2022-07-15 |  |  |  | 902 | 2982 | 2022-09-15 | 2022-09-17 | 330.6 | One way traffic | SF | 6
239.3 | R | 91.3 | ALLENDALE | M-SUPP | 2022-08-22 | 2022-08-24 |  |  |  | 3299 | 21445 | 2022-09-18 | 2022-09-23 | 239.3 | One way traffic, partial restriction for southbound tows while sparred | SF | 41
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-09-24 | 2022-09-25
239.3 | R |  | ALLENDALE | M-SUPP | [7 empty] | 2022-09-26 | 2022-10-06 | 239.3 | One way traffic, partial restriction for southbound tows while sparred
193.6 | R | 45.7 | WHITE CASTLE 1 | M-SUPP | 2022-08-25 | 2022-09-03 |  |  |  | 1511 | 8283 | 2022-10-07 | 2022-10-07 | 193.6 | No deep draft transits during working hours. MSU to fold in at night | SF | 18
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-10-08 | 2022-10-09
193.6 | R |  | WHITE CASTLE 1 | M-SUPP | [7 empty] | 2022-10-10 | 2022-10-15 | 193.6 | No deep draft transits during working hours. MSU to fold in at night
TOW TO KENNER BEND | [11 empty] | 2022-10-16 | 2022-10-16
111.3 | L | 82.3 | KENNER BEND | M-SUPP | 2022-09-23 | 2022-09-24 |  |  |  | 1147 | 5682 | 2022-10-17 | 2022-10-21 | 111.3 | One-way transits with slow bell during working hours. MSU to fold in at night. | SF | 12
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-10-22 | 2022-10-23
70.7 | L | 40.6 | LINWOOD | MAINT | 2022-10-05 | 2022-10-12 |  |  |  | 1218 | 5752 | 2022-10-24 | 2022-10-28 | 70.7 | No transit restrictions during working hours. MSU fold in not required. | SF | 12
TOW TO RAILROAD LANDING M3 | [11 empty] | 2022-10-29 | 2022-10-30
344 | L | -273.3 | RAILROAD LANDING M3 | M-SUPP | 2022-07-10 | 2022-07-12 | 2022-09-23 | 2022-10-29 | 271000 | 3905 | 21600 | 2022-10-31 | 2022-11-04 | 344 | One way traffic - Potential restrictions due to low water | SF | 51
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-11-05 | 2022-11-06
344 | L |  | RAILROAD LANDING M3 | M-SUPP | [7 empty] | 2022-11-07 | 2022-11-18 | 344 | One way traffic - Potential restrictions due to low water
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-11-19 | 2022-11-20
DOWN TIME - OPERATIONAL DELAY/MAINTENANCE | [11 empty] | 2022-11-21 | 2022-11-27
344 | L |  | RAILROAD LANDING M3 | M-SUPP | [7 empty] | 2022-11-28 | 2022-12-01 | 344 | One way traffic - Restrictions on southbound tows 4 barges wide and over
336.8 | L | 7.2 | DEADMAN'S BEND 2020 M2 | M-SUPP | 2022-06-27 | 2022-07-02 | 2022-10-30 | 2022-11-16 | 160000 | 1673 | 8391 | 2022-12-02 | 2022-12-02 | 336.8 | One way traffic - Potential restrictions due to low water | SF | 20
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-12-03 | 2022-12-04
336.8 | L |  | DEADMAN'S BEND 2020 M2 | M-SUPP | [7 empty] | 2022-12-05 | 2022-12-10 | 336.8 | One way traffic - Potential restrictions due to low water
TOW TO RESERVE | [11 empty] | 2022-12-11 | 2022-12-11
138.7 | L | 198.1 | RESERVE | MAINT | 2022-09-15 | 2022-09-22 |  |  |  | 2400 | 12034 | 2022-12-12 | 2022-12-16 | 138.7 | One-way transits with slow bell during working hours. MSU to lay down at night. | SF | 23
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-12-17 | 2022-12-18
138.7 | R |  | RESERVE | CONST | 2022-09-25 | 2022-10-04 | [5 empty] | 2022-12-19 | 2022-12-23 | 138.7 | One-way transits with slow bell during working hours. MSU to lay down at night.
CHRISTMAS BREAK | [11 empty] | 2022-12-24 | 2023-01-01
138.7 | R |  | RESERVE | CONST | 2022-09-25 | 2022-10-04 | [5 empty] | 2023-01-02 | 2023-01-02 | 138.7 | One-way transits with slow bell during working hours. MSU tolay down at night.
99.8 | R | 38.9 | GREENVILLE BEND | CONST | 2022-09-25 | 2022-10-04 |  |  |  | 2600 | 15900 | 2023-01-03 | 2023-01-13 | 99.8 | One-way transits with slow bell during working hours. | SF | 30
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2023-01-14 | 2023-01-15
99.8 | R |  | GREENVILLE BEND | CONST | [7 empty] | 2023-01-16 | 2023-01-17 | 99.8 | One-way transits with slow bell during working hours.
TOW TO WHITE CASTLE | [11 empty] | 2023-01-18 | 2023-01-18
193.4 | R | -93.6 | WHITE CASTLE 2 | M-SUPP | [5 empty] | 1610 | 11506 | 2023-01-19 | 2023-01-27 | 193.4 | No deep draft transits during working hours. MSU to fold in at night | SF | 22
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2023-01-28 | 2023-01-29
192.7 | R | 0.7 | WHITE CASTLE 3 | M-SUPP | 2022-09-09 | 2022-09-14 |  |  |  | 1950 | 12500 | 2023-01-30 | 2023-02-07 | 192.7 | No deep draft transits during working hours. MSU to fold in at night | SF | 24
NO WORK FOR MSU/TOW TO ARK CITY - YELLOW BEND | [11 empty] | 2023-02-08 | 2023-02-11
551.5 | R | -358.8 | ARK CITY - YLLW BND M1 | M-SUPP | 2022-12-15 | 2022-12-29 |  |  |  | 2200 | 8500 | 2023-02-12 | 2023-02-17 | 551.5 | One way traffic - Potential restrictions due to low water | RL | 16
542.5 | R | 9 | MILLER BEND | M-SUPP | 2022-12-30 | 2022-01-15 |  |  |  | 2500 | 9700 | 2023-02-18 | 2023-02-24 | 542.5 | One way traffic - Potential restrictions due to low water | RL | 19
503.5 | R | 39 | SARAH ISL-SECOND PASS | M-SUPP |  |  | 2022-12-15 | 2022-12-31 | 40000 |  | 7386 | 2023-02-25 | 2023-03-02 | 503.5 | Possible river closure for all traffic during daylight hours. | RL | 14
TOW | [11 empty] | 2023-03-03 | 2023-03-03
437 |  | 66.5 | VICKSBURG HARBOR | [8 empty] | 2023-03-04 | 2023-03-04 | 437
[8 empty] | COLUMN TOTAL | 471000 |  | 201545
[11 empty] | SQUARES |  |  | Mile | Reference Locations
| Estimated linear feet per workday | [5 empty] | DISTRICT |  | CY's | LIN. FT | CURRENT | ORIGINAL |  | 955 | Cairo, IL
| Estimated cubic yards grading per workday | [5 empty] | MEMPHIS |  |  |  |  | 0 |  | 889 | New Madrid, MO
1500 | Estimated squares per full workday | [12 empty] | 847 | Caruthersville, MO
876.2826 | Squares Per Calendar Day | [12 empty] | 769 | Richardson Landing Casting Field
1158.3046 | Squares Per Workday | [5 empty] | VICKSBURG |  | 471000 | 26646 | 108443 | 108300 |  | 735 | Memphis, TN
[14 empty] | 663 | Helena, AR
[14 empty] | 537 | Greenville, MS
[14 empty] | 438 | Delta Point Casting Field
[7 empty] | NEW ORLEANS |  |  | 15735 | 93102 | 87700 |  | 437 | Vicksburg, MS
[14 empty] | 364 | Natchez, MS
[14 empty] | 304 | Old River Locks
Gray shade represents completed work | [5 empty] | TOTAL | MVD |  | 471000 | 42381 | 201545 | 196000 |  | 265 | St Francisville Casting Field
[14 empty] | 230 | Baton Rouge, LA
[14 empty] | 95 | New Orleans, LA
[14 empty] | 10 | Venice, LA