## Revetment Schedule w Formulas
U.S. ARMY CORPS OF ENGINEERS, MEMPHIS, VICKSBURG AND NEW ORLEANS | [14 empty] | REVISION DATE
C&S STARTING DATE 10 June 2022 / GRADER STARTING DATE 06 July 2022 / SINKING STARTING DATE 18 JUL 2022 | [14 empty] | 2022-09-15
C&S, GRADING BY KEVIN WILLIAMS / SINKING BY MAURICE GILMORE
REVETMENT OPERATIONS - FY 22-23
LMR MILE | BANK | DISTANCE | LOCATIONS | TYPE WORK | C&S |  | GRADING |  |  | SINKING
[5 empty] | START | FINISH | START | FINISH | CY's | LINEAR FEET ACM | GROSS SQUARES | START | FINISH | LMR MILE | ANTCIPATED TRAFFIC RESTRICTIONS | MLU (ST Francisville, Delta Point, Richardson Landing) | Barge Count | Priority | Top Bank
MILE
437.0 |  |  | MSU conducts training for crew, makes tow / Mandatory Training | [8 empty] | 2022-07-18 | 2022-07-18 | 437.0
TOW | [11 empty] | 2022-07-19 | 2022-07-20
578.6 | R | -141.6 | OZARK M1 | M-SUPP | 2022-06-10 | 2022-06-12 |  |  |  | 2600 | 10169 | 2022-07-21 | 2022-07-29 | 578.6 | One way traffic | RL | 20
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-07-30 | 2022-07-31
578.6 | R |  | OZARK M1 | M-SUPP | [7 empty] | 2022-08-01 | 2022-08-01 | 578.6 | One way traffic | RL
503.5 | R | 75.1 | SARAH ISL-FIRST PASS | M-SUPP | 2022-06-13 | 2022-06-15 |  |  |  | 3000 | 4501 | 2022-08-02 | 2022-08-07 | 503.5 | River closure for southbound traffic > 12 barges during daylight hours | RL | 9
491.7 | R | 11.8 | BALESHED M1 | M-SUPP | 2022-06-16 | 2022-06-22 |  |  |  | 2500 | 7078 | 2022-08-07 | 2022-08-12 | 491.7 | One way traffic | RL | 14
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-08-13 | 2022-08-14
491.7 | R |  | BALESHED M1 | M-SUPP | [7 empty] | 2022-08-15 | 2022-08-16 | 491.7 | One way traffic | RL
428.9 | R | 62.8 | REID BEDFORD M1 | M-SUPP | 2022-06-23 | 2022-06-26 |  |  |  | 1700 | 6219 | 2022-08-17 | 2022-08-24 | 428.9 | One way traffic | RL | 12
345.1 | L | 83.8 | RAILROAD LANDING 2020 M1 | M-SUPP | 2022-07-03 | 2022-07-07 |  |  |  | 3600 | 14608 | 2022-08-25 | 2022-08-26 | 345.1 | One way traffic | SF | 28
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-08-27 | 2022-08-28
345.1 | L |  | RAILROAD LANDING 2020 M1 | M-SUPP | [7 empty] | 2022-08-29 | 2022-09-06 | 345.1 | One way traffic | SF
344.5 | L | 0.6 | RAILROAD LANDING M4 | M-SUPP | 2022-07-08 | 2022-07-09 |  |  |  | 1800 | 7584 | 2022-09-07 | 2022-09-09 | 344.5 | One way traffic | SF | 15
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-09-10 | 2022-09-11
344.5 | L |  | RAILROAD LANDING M4 | M-SUPP | [7 empty] | 2022-09-12 | 2022-09-14 | 344.5 | One way traffic | SF
330.6 | R | 13.9 | BOUGERE | CONST | 2022-07-13 | 2022-07-15 |  |  |  | 700 | 2600 | 2022-09-15 | 2022-09-17 | 330.6 | One way traffic | SF | 5
239.3 | R | 91.3 | ALLENDALE | M-SUPP | 2022-08-22 | 2022-08-24 |  |  |  | 3200 | 17900 | 2022-09-18 | 2022-09-23 | 239.3 | One way traffic | SF | 34
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-09-24 | 2022-09-25
239.3 | R |  | ALLENDALE | M-SUPP | [7 empty] | 2022-09-26 | 2022-10-02 | 239.3 | One way traffic | SF
193.6 | R | 45.7 | WHITE CASTLE 1 | M-SUPP | 2022-08-25 | 2022-09-03 |  |  |  | 1400 | 7200 | 2022-10-03 | 2022-10-07 | 193.6 | No deep draft transits during working hours. MSU to fold in at night | SF | 14
193.4 | R | 0.2 | WHITE CASTLE 2 | M-SUPP | 2022-09-04 | 2022-09-08 |  |  |  | 1610 | 9800 | 2022-10-07 | 2022-10-07 | 193.4 | No deep draft transits during working hours. MSU to fold in at night | SF | 19
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-10-08 | 2022-10-09
193.4 | R |  | WHITE CASTLE 2 | M-SUPP | [7 empty] | 2022-10-10 | 2022-10-15 | 193.4 | No deep draft transits during working hours. MSU to fold in at night | SF
111.3 | L | 82.1 | KENNER BEND | M-SUPP | 2022-09-23 | 2022-09-24 |  |  |  | 1180 | 5600 | 2022-10-16 | 2022-10-20 | 111.3 | One-way transits with slow bell during working hours. MSU to fold in at night. | SF | 11
NO WORK FOR MSU - OFF DAYS & TOW TO RAILROAD LANDING M3 | [11 empty] | 2022-10-21 | 2022-10-23
344 | L | -232.7 | RAILROAD LANDING M3 | M-SUPP | 2022-07-10 | 2022-07-12 | 2022-09-23 | 2022-10-21 | 221000 | 4600 | 18400 | 2022-10-24 | 2022-11-04 | 344 | One way traffic | SF | 35
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-11-05 | 2022-11-06
344 | L |  | RAILROAD LANDING M3 | M-SUPP | [7 empty] | 2022-11-07 | 2022-11-07 | 344 | One way traffic | SF
336.8 | L | 7.2 | DEADMAN'S BEND 2020 M2 | M-SUPP | 2022-06-27 | 2022-07-02 | 2022-10-22 | 2022-10-31 | 140000 | 2300 | 8900 | 2022-11-08 | 2022-11-14 | 336.8 | One way traffic | SF | 17
TOW TO WHITE CASTLE 3 | [11 empty] | 2022-11-15 | 2022-11-15
192.7 | R | 144.1 | WHITE CASTLE 3 | M-SUPP | 2022-09-09 | 2022-09-14 |  |  |  | 1950 | 12500 | 2022-11-16 | 2022-11-18 | 192.7 | No deep draft transits during working hours. MSU to fold in at night | SF | 24
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-11-19 | 2022-11-20
192.7 | R |  | WHITE CASTLE 3 | M-SUPP | 2022-09-09 | 2022-09-14 | [5 empty] | 2022-11-21 | 2022-11-26 | 192.7 | No deep draft transits during working hours. MSU to fold in at night | SF
138.7 | L | 54 | RESERVE | MAINT | 2022-09-15 | 2022-09-22 |  |  |  | 2400 | 11900 | 2022-11-27 | 2022-12-02 | 138.7 | One-way transits with slow bell during working hours. MSU to fold in at night. | SF | 23
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-12-03 | 2022-12-04
138.7 | L |  | RESERVE | MAINT | [7 empty] | 2022-12-05 | 2022-12-07 | 138.7 | One-way transits with slow bell during working hours. MSU to fold in at night. | SF
99.8 | R | 38.9 | GREENVILLE BEND | CONST | 2022-09-25 | 2022-10-04 |  |  |  | 2600 | 15900 | 2022-12-08 | 2022-12-16 | 99.8 | One-way transits with slow bell during working hours for vessels with draft 40 feet or greater. MSU to fold in at night | SF | 30
NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-12-17 | 2022-12-18
99.8 | R |  | GREENVILLE BEND | CONST | [7 empty] | 2022-12-19 | 2022-12-21 | 99.8 | One-way transits with slow bell during working hours for vessels with draft 40 feet or greater. MSU to fold in at night | SF
70.7 | L | 29.1 | LINWOOD | MAINT | 2022-10-05 | 2022-10-12 |  |  |  | 1120 | 6900 | 2022-12-22 | 2022-12-23 | 70.7 | No transit restrictions during working hours. MSU fold in not required. | SF | 13
CHRISTMAS BREAK | [11 empty] | 2022-12-24 | 2022-12-26
70.7 | L |  | LINWOOD | MAINT | [7 empty] | 2022-12-27 | 2022-12-29 | 70.7 | No transit restrictions during working hours. MSU fold in not required. | SF
TOW AND NO WORK FOR MSU - OFF DAYS | [11 empty] | 2022-12-30 | 2023-01-02
551.5 | R | -480.8 | ARK CITY - YELLW BND M1 | M-SUPP | 2022-11-01 | 2022-11-10 |  |  |  | 2200 | 8500 | 2023-01-03 | 2023-01-08 | 551.5 | One way traffic | RL | 16
542.5 | R | 9 | MILLER BEND | M-SUPP | 2022-11-11 | 2022-11-18 |  |  |  | 2500 | 9700 | 2023-01-09 | 2023-01-15 | 542.5 | One way traffic | RL | 19
503.5 | R | 39 | SARAH ISL-SECOND PASS | M-SUPP |  |  |  |  | 40000 |  | 7386 | 2023-01-16 | 2023-01-21 | 503.5 | Possible river closure for all traffic during daylight hours | RL | 14
TOW | [11 empty] | 2023-01-22 | 2023-01-22
437 |  | 66.5 | VICKSBURG HARBOR | [8 empty] | 2023-01-23 | 2023-01-23 | 437
|  | 0 | [5 empty] | COLUMN TOTAL | 401000 |  | 193345
[11 empty] | SQUARES |  |  | Mile | Reference Locations
| Estimated linear feet per workday | [5 empty] | DISTRICT |  | CY's | LIN. FT | CURRENT | ORIGINAL |  | 955 | Cairo, IL
| Estimated cubic yards grading per workday | [5 empty] | MEMPHIS |  |  |  |  | 0 |  | 889 | New Madrid, MO
1500 | Estimated squares per full workday | [12 empty] | 847 | Caruthersville, MO
1017.6053 | Squares Per Calendar Day | [12 empty] | 769 | Richardson Landing Casting Field
1255.487 | Squares Per Workday | [5 empty] | VICKSBURG |  | 401000 | 27500 | 105645 | 108300 |  | 735 | Memphis, TN
[14 empty] | 663 | Helena, AR
[14 empty] | 537 | Greenville, MS
[14 empty] | 438 | Delta Point Casting Field
[7 empty] | NEW ORLEANS |  |  | 15460 | 87700 | 87700 |  | 437 | Vicksburg, MS
[14 empty] | 364 | Natchez, MS
[14 empty] | 304 | Old River Locks
Gray shade represents completed work | [5 empty] | TOTAL | MVD |  | 401000 | 42960 | 193345 | 196000 |  | 265 | St Francisville Casting Field
[14 empty] | 230 | Baton Rouge, LA
[14 empty] | 95 | New Orleans, LA
[14 empty] | 10 | Venice, LA

## REF (hidden)
Off Days | SQ/Day | 1500 | Job Sites |  | Days
2022-07-16 |  |  | TOW TO OZARK |  | 2 | 2 |  |  |  | 2022-07-11
2022-07-17 |  | First Job | OZARK M1 | 10300 | 6.8667 | 8 | 2022-07-19 | 2022-07-26 |  | 2022-07-18
2022-07-30 |  |  | SARAH ISL-POS PT M3 | 12000 | 8 | 9 | 2022-07-27 | 2022-08-06
2022-07-31 |  |  | BALESHED M1 | 10000 | 6.6667 | 7 | 2022-08-07 | 2022-08-15
2022-08-13 |  |  | REID BEDFORD M1 | 6500 | 4.3333 | 5 | 2022-08-16 | 2022-08-20
2022-08-14 |  |  | RAILROAD LANDING 2020 M1 | 14400 | 9.6 | 10 | 2022-08-21 | 2022-09-01 | 0
2022-08-27 |  |  | RAILROAD LANDING M4 | 7000 | 4.6667 | 5 | 2022-09-02 | 2022-09-06
2022-08-28 |  |  | RAILROAD LANDING M3 | 18400 | 12.2667 | 13 | 2022-09-07 | 2022-09-21
2022-09-10 |  |  | DEADMAN'S BEND 2020 M2 | 8900 | 5.9333 | 6 | 2022-09-22 | 2022-09-29
2022-09-11 |  |  | BOUGERE | 2600 | 1.7333 | 2 | 2022-09-30 | 2022-10-01
2022-09-24 |  |  | ALLENDALE | 17900 | 11.9333 | 12 | 2022-10-02 | 2022-10-15
2022-09-25 |  |  | WHITE CASTLE 1 | 7200 | 4.8 | 5 | 2022-10-16 | 2022-10-20
2022-10-08 |  |  | WHITE CASTLE 2 | 9800 | 6.5333 | 7 | 2022-10-21 | 2022-10-29
2022-10-09 |  |  | WHITE CASTLE 3 | 12500 | 8.3333 | 9 | 2022-10-30 | 2022-11-09
2022-10-22 |  |  | RESERVE | 11900 | 7.9333 | 8 | 2022-11-10 | 2022-11-17
2022-10-23 |  |  | KENNER BEND | 5600 | 3.7333 | 4 | 2022-11-18 | 2022-11-23
2022-11-05 |  |  | GREENVILLE BEND | 15900 | 10.6 | 11 | 2022-11-24 | 2022-12-06
2022-11-06 |  |  | LINWOOD | 6900 | 4.6 | 5 | 2022-12-07 | 2022-12-11
2022-11-19 |  |  | ARK CITY - YELLW BND M1 | 8500 | 5.6667 | 6 | 2022-12-12 | 2022-12-19
2022-11-20 |  |  | MILLER BEND | 9700 | 6.4667 | 7 | 2022-12-20 | 2022-12-28
2022-12-03
2022-12-04
2022-12-17
2022-12-18
2022-12-25
2022-12-26
2022-12-31
2023-01-01
2023-01-14
2023-01-15
2023-01-28
2023-01-29
2023-02-11
2023-02-12
2023-02-25
2023-02-26
2023-03-11
2023-03-12
2023-03-25
2023-03-26
2023-04-08
2023-04-09
2023-04-22
2023-04-23
2023-05-06
2023-05-07

## Sheet1 (hidden)
2022 - 2023 REVETMENT SEASON
MILE | BANK | JOBSITE | LINEAR FT | SQUARES | START | END | MILE
578.6 | R | OZARK M1 | 2600 | 10169 | 2022-07-21 | 2022-07-29 | 578.6
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-07-30 | 2022-07-31
578.6 | R | OZARK M1 |  |  | 2022-08-01 | 2022-08-01 | 578.6
503.5 | R | SARAH ISL-FIRST PASS | 3000 | 4501 | 2022-08-02 | 2022-08-07 | 503.5
491.7 | R | BALESHED M1 | 2500 | 7078 | 2022-08-07 | 2022-08-12 | 491.7
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-08-13 | 2022-08-14
491.7 | R | BALESHED M1 |  |  | 2022-08-15 | 2022-08-16 | 491.7
428.9 | R | REID BEDFORD M1 | 1700 | 6219 | 2022-08-17 | 2022-08-24 | 428.9
345.1 | L | RAILROAD LANDING 2020 M1 | 3600 | 14608 | 2022-08-25 | 2022-08-26 | 345.1
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-08-27 | 2022-08-28
345.1 | L | RAILROAD LANDING 2020 M1 |  |  | 2022-08-29 | 2022-09-06 | 345.1
344.5 | L | RAILROAD LANDING M4 | 1800 | 7584 | 2022-09-07 | 2022-09-09 | 344.5
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-09-10 | 2022-09-11
344.5 | L | RAILROAD LANDING M4 |  |  | 2022-09-12 | 2022-09-14 | 344.5
330.6 | R | BOUGERE | 700 | 2600 | 2022-09-15 | 2022-09-17 | 330.6
239.3 | R | ALLENDALE | 3200 | 17900 | 2022-09-18 | 2022-09-23 | 239.3
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-09-24 | 2022-09-25
239.3 | R | ALLENDALE |  |  | 2022-09-26 | 2022-10-02 | 239.3
193.6 | R | WHITE CASTLE 1 | 1400 | 7200 | 2022-10-03 | 2022-10-07 | 193.6
193.4 | R | WHITE CASTLE 2 | 1610 | 9800 | 2022-10-07 | 2022-10-07 | 193.4
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-10-08 | 2022-10-09
193.4 | R | WHITE CASTLE 2 |  |  | 2022-10-10 | 2022-10-15 | 193.4
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
|  | NO WORK FOR MSU - OFF DAYS |  |  | 2022-12-17 | 2022-12-18
99.8 | R | GREENVILLE BEND |  |  | 2022-12-19 | 2022-12-21 | 99.8
|  | CHRISTMAS BREAK |  |  | 2022-12-24 | 2022-12-26
70.7 | L | LINWOOD |  |  | 2022-12-27 | 2022-12-29 | 70.7
|  | #REF! |  |  | #REF! | #REF!
551.5 | R | ARK CITY - YELLW BND M1 | 2200 | 8500 | 2023-01-03 | 2023-01-08 | 551.5
|  | #REF! |  |  | #REF! | #REF!
|  | #REF! |  |  | #REF! | #REF!
542.5 | R | MILLER BEND | 2500 | 9700 | 2023-01-09 | 2023-01-15 | 542.5
503.5 | R | SARAH ISL-SECOND PASS |  | 7386 | 2023-01-16 | 2023-01-21 | 503.5
|  | TOW |  |  | 2023-01-22 | 2023-01-22
437 | 0 | VICKSBURG HARBOR |  |  | 2023-01-23 | 2023-01-23 | 437
| 43590 | Total Squares Sunk as of 8/11 | 663 | Helena | 265 | St Francisville
| 69655 | Total Squares Left to Sink | 537 | Greenville | 230 | Baton Rouge
| 38.49% | Percent Complete | 437 | Vicksburg | 95 | New Orleans
|  |  | 364 | Natchez | 10 | Venice